## Decision Item List
HR Upgrade or Advisory Group Meeting Date | Topic | Discussion/Action Required | Decision | Completed
Upgrade Group Meeting: 4/1/2014 | Visual identification and Ethnicity Data | ES - Ensure information is stored in CIW
| Home Department and Campus Box | Is this something that needs to be carried forward? Regardless of where it is stored, it needs to be queried. Need to work with campus IT to ensure they pull from correct fields as this is used for IDs and emails | Home Department will be tied to whichever job is designated the 'Primary Job' in Job Data. Campus Box will be tied to Position Info and will be stored in the Mail Drop ID of the Primary Job
| On-line I-9 in HCM | Will new ee address, name, SSN populate from Taleo? - ES will follow up. | Campus would like to move forward with a paperless process and ability to upload documents. Campus Working group will be established after July when the CU Data is built into a Testing Sandbox
| e-Verify | Is this something we want to do? Campuses interested. Need to follow up with Missouri as they are a multi-campus and are utilizing this function | Research is still being conducted on this capability and will be evaluated further with Campus Working Group in July
| Job Codes and Compra-ratios-Manager Dashboard | In HCM salary ranges are tied to job codes. Campuses would like to allow managers to see compra-ratios and use for salary and merit adjustments but need to see functionality comparison of Kenexa and HCM. Comparison document will be prepared for May meeting | CU does not own the eCompensation module and the campuses will use Kenexa for salary analysis and determining salary ranges that will be uploaded into individual Position Profiles
| Dashboard | Who should have access? Does it show vacant positions? | Under discussion with HR Directors
Advisory Group Meeting: 4/8/2014 | Campus Box | Investigate if this can be tied to Location | See Decision Item above.
| Primary Job | Need to verify that users will be able to see other appointments outside of their security level. | Continue to research once CU database is available in July.
| Email and System access | Will discuss with Campus IT offices
| Dashboard | Who should have access? Does it show vacant positions? | Under discussion with HR Directors
Upgrade Group Meeting: 5/1/2014 | Need for Position Notes? | Is this required, necessary, or used? Some staff use this function. | Verify that notes can be added to the Approval process.
| Eliminate Go To Position Funding link | Staff will still have access to these pages, however entering and updating funding will be managed through a different process | 9.2 has the capability to create Forms/Templates for multiple actions, e.g., new hire, promotion, transfer, chg in funding or FTE, termination. These will be used to populate the fields without HR Business Partners or HR staff going into multiple screens (e.g, position data, job data, personal information). Samples will be available when testing starts in December, 2014.
| Eliminate customized position requirements from Position Data | This information will move to Position Profiles and the Position Data will be kept as delivered. | Unique position requirements such as essential services, Classified Staff Supervision, HIPAA and Hazardous Material requirements will be built into individual Position Profiles.
| Percent of Time | This is currently maintained in Job and Position data. This is used by Research Faculty | This will be a customization that will be retained in Job data but will not be part of Position data as this is tied to a 'person's' effort not the postion. FTE in Positon Data will reflect the budgeted FTE for the postion
| Action Reasons | HR Staff worked to reduce the number of action reasons. | A campus working group will discuss further when the CU database is available and action forms are created. Definitions will be developed so HR Staff and Business Partners have a clear understanding of the meaning of each action reason
| Compensation and current use of multiple positions | Discussed our current practice of using multiple positions for additional pay. Could this be streamlined by using additional earnings codes and the Multiple Components of Pay functionality | Further discussion regarding additional compensation and how this is processed with continue when the CU data base is available
Advisory Group Meeting: 5/15/2014 | This meeting covered the Position and Job Fit/Gaps that were discussed in the Upgrade Meeting on 5/1/14
| ACA | A question was raised as to what fields are used for tracking hours for the Affordable Care Act (ACA) | Standard Hours drives benefits and Employee Services will ensure hours reported are in sinc for ACA purposes
| Required need to have funding to create a position |  | Controllers do not see this as necessary; however, further discussion with Sponsored Programs will be needed.
| 9.2 functionality for tracking Faculty Tenure and Faculty Events | UCD and UCCS were interested in this functionality to track tenure timelines as well as faculty events such as yearly reviews of publications and journals, student counseling, committees, activities, administrative posts, etc | Further discussion with all campuses will occur once the CU database is available.
| Compensation | This discussion was consistent with feedback from the Upgrade Group Meeting | Further discussion will occur once the CU database is available