## FY 2021
Last updated: |  | Dates related to State deadlines are highlighted in green and have been reviewed/adjusted based on State's open/close calendar
2021-07-30 |  | Dates related to the CORE feeds and extracts highlighted in orange
Date | # | FY2021 TASK DESCRIPTION | Date Changed | Budget | Campus | Other | OUC_Acct | OUC_Fin | ES | PSC | UIS_CIW | CU Medicine
2021-04-30 |  | Fran Chapman sends updated mandatory Fiscal Certification population (including PIs) to the Campus Controllers for final review |  |  | X |  |  | X
2021-04-30 |  | Last day to submit requisitions for purchases requiring DOCUMENTED QUOTES. (These are purchases of goods $10,001-$500,000 using federal or nonfederal funds; and purchases of services $10,001-$500,000 using federal funds or $50,001-$500,000 using non-federal funds). |  |  | X |  |  |  |  | X
2021-04-30 |  | OUC website updated with FY2021 Year-End Processing and Deadlines (www.cu.edu/controller) |  |  | X | X | X |  |  | X
2021-04-30 |  | Begin Payroll Suspense review and cleanup |  |  | X |  |  |  | X
2021-04-30 |  | Expand HR message to remind how to prevent funding distribution suspense |  |  | X |  |  | X | X
2021-04-30 |  | Update Apply to Next Fiscal Year dates for Funding Entries and communicate funding update to campus payroll liasons | [6 empty] | X
2021-05-14 |  | Need to test PO roll forward |  |  | X | [5 empty] | X
2021-05-14 |  | UBIT estimates for entire fiscal year ending 6/30/2021 due to Tax Director |  |  | X | X
2021-05-14 |  | Last day to submit all other high dollar (over $10,000) PO/SPO requisitions using FY2021 funds |  |  | X |  |  |  |  | X
2021-05-24 |  | Deadline for the reviewed final population to be returned to Fran Chapman in the OUC |  |  | X |  |  | X
2021-05-28 |  | General Ledger Closing and CORE Interface Calendar to be created and inform UIS/ES once posted to the OUC website |  |  |  |  | X | X | X |  | X
2021-05-28 |  | CU Boulder & UCCS Athletics to begin survey staff for Gift In Kind process |  |  | X
2021-05-31 |  | HOLIDAY |  | X | X | X | X | X | X | X | X | X
2021-06-01 |  | Updated Exhibit listing and instructions posted on the OSC website |  |  | X |  | X
2021-06-01 |  | Generate spring semester ePERs |  |  | X |  |  | X
2021-06-01 |  | FY2022 Detail Calendars need to be built including 10, DT, D1 | [5 empty] | X
2021-06-01 |  | Email to Officers and Delegates regarding population review and setting due dates |  |  | X |  |  | X
2021-06-07 |  | Obtain Fringe percentage updates from campuses and update tables |  |  | X |  |  |  | X
2021-06-07 |  | Request Benefits Team update accrual rates if necessary due to changes in FICA/PERA | [6 empty] | X
2021-06-11 | 1 | To ensure payment in FY2021, last day to provide supplier information to PSC to request new supplier or update existing supplier - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-11 | 1 | To ensure payment in FY2021, last day to submit paper forms (PAs, NRIs and SSPs) to the PSC (APInvoice@cu.edu) - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-11 | 1 | To ensure payment in FY2021, last day to provide campus approval for Payment Vouchers (PV) in Marketplace - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-11 | 1 | To ensure payment in FY2021 (subject to payment terms), last day to submit vendor invoices to the PSC (APInvoice@cu.edu) - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-11 | 2 | Moratorium on new account code requests and new June allocation group requests (permanent) FY2021 |  |  | X |  | X | X
2021-06-11 | 2 | Moratorium on Org tree changes begins |  |  | X |  |  | X
2021-06-11 | 2 | Moratorium on expense purpose code changes begins |  |  | X |  | X | X
2021-06-11 |  | CU Medicine to provide estimate to CU Denver |  |  | X | [6 empty] | X
2021-06-11 |  | Last day to notify OUC Finance if continuing budgets are ready for roll forward |  | X | X |  |  | X
2021-06-11 |  | Ensure HR calendar for FY2022 for PeopleSoft is updated (HR YEAREND and HR PeopleSoft CALENDAR) PET |  |  | X |  |  |  | X |  | X
2021-06-14 |  | Evaluate CORE cash balance (account 1100), ensure funds are transferred prior to month end |  |  | X |  | X
2021-06-14 |  | Distribute year-end templates (for report footnotes & exhibits) |  | X | X |  | X |  | X
2021-06-15 |  | Create HCM Development request to set accounting date on last FY BW and OC to 6/30 | [6 empty] | X
2021-06-15 |  | Update Compensated Absences report retirement rate | [6 empty] | X
2021-06-17 |  | 5pm deadline to upload and approve time for BW PPE 6/12 |  |  | X |  |  |  | X
2021-06-17 |  | 5pm approval deadline for Position Data, Funding, and Job Data |  |  | X
2021-06-18 | 1 | Last day to close POs so that they don't roll forward into the new year. Send request to Changeorder@cu.edu. Deadline 6pm |  |  | X |  |  | X |  | X | X
2021-06-18 | 1 | Last day to provide campus approval for procurement card expense reports - Deadline 6pm (rest will have to be accrued) |  |  | X |  |  |  |  | X
2021-06-18 | 1 | SPOs that need to roll forward into the new year must have at least $1 balance |  |  | X |  |  |  |  | X
2021-06-18 | 1 | Last day to request increases to SPOs. Send request to Changeorder@cu.edu. Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-18 | 2 | Processing BW PPE 6/12 (earn dates 5/30-6/12) - All Day - pays on 6/25 |  |  | X |  |  |  | X |  | X
2021-06-18 | 3 | To ensure payment in FY2021, last day to provide campus approval for employee travel/expense reimbursements in Concur - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-18 | 3 | To ensure payment in FY2021, last day to provide campus approval for non-employee travel/expense reimbursements in Concur - Deadline 6pm |  |  | X |  |  |  |  | X
2021-06-18 |  | Processing MON PPE 6/30 HR Production Available (5pm on 6/18 through 6/23) |  |  | X |  |  |  | X |  | X
2021-06-18 |  | CU Boulder & UCCS Athletics - last day to complete survey for Gift In Kind |  |  | X
2021-06-21 |  | FY2022 Long Bill including Capital Construction will be approved and interfaced to CORE, all documents will load as approved, and any rejections will be reviewed and submitted by OSC |  | X | X |  | X
2021-06-21 |  | FY2022 Special Bills will be approved and interfaced to CORE, all documents will load as approved, and any rejections will be reviewed and submitted by OSC |  | X | X |  | X
2021-06-21 |  | Run Payroll Register for BW PPE 6/12 - pays on 6/25 |  |  | X |  |  |  | X
2021-06-23 | 1 | Bursars 4:30 pm cutoff for check refunds |  |  | X | [5 empty] | X
2021-06-23 | 2 | Run Payroll Register Report for MON PPE 6/30 - pays on 6/30 |  |  | X |  |  |  | X
2021-06-23 |  | Check general fund HR encumbrances - no encumbrances for the general fund |  |  | X |  |  | X | X |  | X
2021-06-23 |  | Noon - CUF deadline for gift transfer requests >= $500,000 for 6/30 wire |  |  | X | X |  |  |  |  | X
2021-06-23 |  | First day all batch processing exceptions are Call Jobs | [8 empty] | X
2021-06-25 |  | BW 06/12 Pay Day |  |  | X |  |  |  | X |  | X
2021-06-25 |  | Request Prod Services hold PET job on OUC FYE Close Dates | [6 empty] | X |  | X
2021-06-25 |  | Last day to submit requests to cancel AP checks - Deadline Noon |  |  | X |  |  |  |  | X
2021-06-28 |  | Bursars 4:30 pm cutoff for direct deposit refunds, demand warrants, and refund cancellations |  |  | X | [5 empty] | X
2021-06-29 |  | Change PAY source to require approval (OC processes on 7/1 and BW on 7/6) | [5 empty] | X |  |  | X
2021-06-29 |  | ACHs (debits & credits) related to FY2021 must be processed in CORE and ready for State Treasury's approval no later than 11am on this date |  |  | X |  | X
2021-06-29 |  | Position Funding roll over |  |  | X |  |  | X | X |  | X
2021-06-30 | 0 | Run June Payroll Encumbrance for LDOM (12:30am Automic scheduled) |  |  | X |  |  | X | X |  | X
2021-06-30 | 1 | 5pm deadline for any handdrawn payroll checks to be recorded in FY2021 (OC 06/24/21) |  |  | X |  |  | X | X |  | X
2021-06-30 | 1 | After nightly processing run PO roll forward processes detailed in the FYE SQL Setup and Processing document | [5 empty] | X |  |  | X
2021-06-30 | 2 | Invoices sent to PSC (APInvoice@cu.edu) on July 2 by noon are automatically considered FY2021 business/accrued. Invoices for FY2022 business should NOT be sent to the PSC until July 7 and after |  |  | X |  |  |  |  | X
2021-06-30 | 2 | Bursars cash office will close at 5pm (4pm for UCCS, 4:30 for CU Boulder) |  |  | X | [5 empty] | X
2021-06-30 | 2 | Open all periods for the new fiscal year for the Actuals ledger in PeopleSoft |  |  | X |  |  | X |  |  | X
2021-06-30 | 3 | MON June Pay Day |  |  | X |  |  |  | X |  | X
2021-06-30 | 3 | PET accounting date set to 6/30 until 7/14 |  |  | X |  |  | X | X |  | X
2021-06-30 | 3 | Funding changes to impact payroll encumbrances for FY2021 can be processed until 6pm |  |  | X |  |  | X | X |  | X
2021-06-30 | 4 | Physical inventory of consumable goods must be completed on or before this date |  |  | X
2021-06-30 | 4 | Goods and services must be physically received by this date in order to be accounted for in FY2021 |  |  | X |  |  |  |  | X
2021-06-30 | 4 | A count of petty cash and change funds should be completed by this date |  |  | X
2021-06-30 | 5 | State Treasury cash cutoff, walk-in deposits must be at the State Treasurer's Office by 2pm to be recorded in balance sheet cash account 1100-Operating Cash for FY2021 |  |  | X |  | X
2021-06-30 | 5 | For continuation of expiring capital construction project appropriations, all encumbrances (contracts) must be effective on or before this date |  |  | X |  | X
2021-06-30 | 6 | Last day to run batch Warrant/ACH for FY2021 after pay cycle in nightly |  |  | X |  |  | X |  |  | X
2021-06-30 |  | Actuarial reports due from AON to OUC for OPEB and AMP |  |  | X |  | X |  | X
2021-06-30 |  | Close date for due dates and population review for Fiscal Certification |  |  | X |  |  | X
2021-06-30 |  | Email sent to mandatory Fiscal Certification population |  |  | X |  |  | X
2021-06-30 |  | Add ORG/Account Tree FY2022 |  |  | X |  | X | X |  |  | X
2021-06-30 |  | Roll forward project budgets in PeopleSoft and expenses for processing in July OUC Finance online during the day |  |  | X |  |  | X
2021-06-30 |  | Update Journal Gen Templates for AP, AM, TR, and GM to Use Transaction Accounting Date and Retain Date | [5 empty] | X
2021-06-30 |  | Run of FIN_WKNIGHT will occur including refresh at 6pm | [5 empty] | X |  |  | X
2021-06-30 |  | Bursars closed for business by 5pm (turn off Nelnet, Tuition Calc, COF, table validation, Run final payment applier) GL Interface run after the payment applier is finished |  |  | X | [5 empty] | X
2021-06-30 |  | Processing OC 06/24/21 Payroll - pays on 7/2 (Hold post processing to FIN until after close) - accounting date must be 6/30 |  |  | X |  |  |  | X |  | X
2021-07-01 | 1 | Each campus to run the Scholarship Allowance detail and summary reports |  |  | X
2021-07-01 | 1 | CORE FY2021 Period 13 opens, however continue to feed to Period 12 |  |  |  |  | X |  |  |  | X
2021-07-01 | 2 | YE Template due from Employee Services and PBA (1st part) to OUC |  |  |  |  | X | X | X
2021-07-01 | 2 | Run July Payroll Encumbrance for FDOM |  |  | X |  |  |  | X |  | X
2021-07-01 | 3 | Employee Services to supply OUC with Early Retirement Incentive Plan payout details, OUC to forward to applicable campuses |  |  | X |  | X |  | X
2021-07-01 |  | Employee Services to provide PBA with their section of overpayment log; PBA to send entire log to accounting@cu.edu for distribution to campuses for reclass entries |  |  | X |  | X |  | X
2021-07-01 |  | 5pm deadline to upload and approve time for BW PPE 6/26 |  |  | X |  |  |  | X
2021-07-01 |  | 5pm approval deadline for Position Data, Funding, and Job Data |  |  | X
2021-07-02 | 1 | Student Financials snapshot data is available in Cognos by Noon |  |  | X | [5 empty] | X
2021-07-02 | 1 | Last day for campuses to allocate Procurement Card reports for accruals - Deadline 6pm |  |  | X |  |  |  |  | X
2021-07-02 | 1 | Last day to provide campus approval for PVs in Marketplace for FY2021 - Deadline 6 pm |  |  | X |  |  |  |  | X
2021-07-02 | 2 | PSC to provide procurement card CU to CU transaction report to campuses for elimination |  |  | X |  |  |  |  | X
2021-07-02 | 2 | Processing BW PPE 6/26 (earn dates 6/13 - 6/26) - pays on 7/9 - accounting date must be 6/30 |  | X | X |  |  |  | X |  | X
2021-07-02 | 3 | OUC to book the payroll accrual (shift) for BW PPE 6/26 |  |  | X |  | X |  | X
2021-07-02 |  | OUC to book the payroll accrual (shift) for OC 06/24/21 |  | X | X |  | X |  | X |  | X
2021-07-02 |  | Request bank statements for completion of Risk Classification on Exhibit M |  |  | X |  | X
2021-07-02 |  | Send email reminders for Internal Receivables/Payables | [5 empty] | X
2021-07-05 |  | HOLIDAY |  | X | X | X | X | X | X | X | X | X
2021-07-06 |  | Run Payroll Register for BW PPE 6/26 - pays on 7/9 |  |  | X |  |  |  | X
2021-07-06 |  | Mandatory Fiscal Certification commences |  |  | X |  |  | X
2021-07-06 |  | Voluntary certification is made available in the portal |  |  | X |  |  | X
2021-07-06 |  | Data for Marketplace (MKT) and Procurement Card (ESP) accruals pulled | [5 empty] | X |  | X | X
2021-07-07 |  | Begin response to State receivable/payable confirmations 7/7 - 8/11 (OUC does for all campuses, email to accounting@cu.edu) |  |  | X |  | X |  |  |  | X
2021-07-07 |  | 1st Preliminary close for campus input (Period 12) - All journals must be approved by 6pm |  | X | X | X | X | X | X | X | X | X
2021-07-07 |  | Bursars: Review journal feed to ensure that all related journals are posted |  |  | X | [5 empty] | X
2021-07-07 |  | Update CORE open period to CORE Period 12 |  |  |  |  | X
2021-07-07 |  | Update AP Journal Generator template to use current date after nightly processing | [5 empty] | X
2021-07-08 | 0 | USER ALERT : No FY2021 journals should be approved or manually posted (new fiscal year exemption) |  | X | X | X | X | X | X | X |  | X
2021-07-08 | 1 | Journals not posted will be updated to the open adjustment period |  |  | X |  |  | X |  |  | X
2021-07-08 | 2 | Run 1st close (Period 12) allocations in PeopleSoft for year-end |  | X |  |  |  | X |  |  | X
2021-07-08 | 2 | Do not run Revenue Reclass |  | X |  |  |  | X |  |  | X
2021-07-08 | 3 | Transmit JVA1 file for 1st June feed to CORE (Period 12) upon approval by OUC |  |  |  |  | X |  |  |  | X
2021-07-08 | 4 | Run Detail PeopleSoft Extract & JVA1 file after FY2021 processing for 1st June CORE feed (CORE Period 12) |  |  |  |  | X |  |  |  | X
2021-07-08 | 5 | Open Period 996 after close completed |  |  | X |  |  | X |  |  | X
2021-07-09 | 1 | Check CORE for feed errors |  |  |  |  | X
2021-07-09 | 2 | Distribute detail CORE PeopleSoft Extract Report to campuses |  |  | X |  | X
2021-07-09 | 3 | Run CORE Extracts A, C (CORE_AC_EXTRACT) at 8am Period 12 FY2021 |  |  | X |  | X |  |  |  | X
2021-07-09 |  | FY2022 Long Bill will be reconciled and a coded Long Bill will be provided by OSC to HEFC at OUC |  | X | X |  | X
2021-07-09 |  | 1st Close (Period 12) Reports available on demand in the reporting system after 8am |  |  | X |  | X
2021-07-09 |  | OUC will provide compensated absence information to campuses to record in PeopleSoft before 2nd close (Period 996) |  |  | X |  | X
2021-07-09 |  | Post Procurement Card (ESP) accrual entry (RUN BEFORE ALLOCATIONS) |  |  | X |  |  | X |  | X
2021-07-09 |  | Run budget-to-actual roll forwards
2021-07-09 |  | Known errors file update to OUC |  |  | X |  | X
2021-07-11 |  | Special run of FIN_WKNIGHT will occur including refresh at 6pm |  |  | X |  |  | X |  |  | X
2021-07-12 |  | Exhibit K3 (status of prior year audit findings) due to the OUC (to send to the OSC) |  |  | X |  | X |  |  |  | X
2021-07-12 |  | Post Marketplace (MKT) accrual entry (RUN BEFORE ALLOCATIONS) |  |  | X |  |  | X |  | X
2021-07-13 |  | Run budget-to-actual roll forwards | [5 empty] | X |  |  | X
2021-07-14 |  | Last day to create & approve PET FY2021 business - Deadline 6pm |  |  | X |  |  |  | X
2021-07-14 |  | 2nd Preliminary close for campus input (Period 996) - All journals must be approved by 6pm |  | X | X | X | X | X | X | X | X | X
2021-07-15 | 0 | USER ALERT : No FY2021 journals should be approved or manually posted (New fiscal year exemption) |  | X | X | X | X | X | X | X | X | X
2021-07-15 | 1 | Run 2nd close (Period 996) incremental allocations against Period 996 (No PIE) | [5 empty] | X |  |  | X
2021-07-15 | 1 | Do not run Revenue Reclass | [5 empty] | X |  |  | X
2021-07-15 | 2 | Open Period 997 after close completed | [5 empty] | X |  |  | X
2021-07-15 | 3 | Journals not approved will be updated to the open adjustment period |  |  | X |  |  | X |  |  | X
2021-07-15 | 4 | Reminder : No accruals to be booked without prior approval of appropriate campus controller |  |  | X
2021-07-15 | 5 | Inactivate Fixed Amount Allocations | [5 empty] | X |  |  | X
2021-07-15 | 6 | Transmit JVA1 file for 2nd June feed to CORE (CORE Period 12) by 6pm upon OUC approval |  |  |  |  | X |  |  |  | X
2021-07-15 | 7 | Run Detail PeopleSoft Extract & JVA1 file after FY2021 processing for 2nd June CORE feed (CORE Period 12) |  |  |  |  | X |  |  |  | X
2021-07-15 |  | CDHE report of expenditures due to CDHE (email copies to accounting@cu.edu) |  |  | X |  | X
2021-07-15 |  | Remove funding entry apply to next fiscal year | [6 empty] | X
2021-07-16 | 0 | USER ALERT : All unapproved FY2021 journals need to be reviewed by the campus controllers |  | X | X | X
2021-07-16 | 1 | Check CORE for feed errors |  |  |  |  | X
2021-07-16 | 2 | Distribute detail CORE PeopleSoft Extract Report to campuses |  |  | X |  | X
2021-07-16 | 3 | Run CORE Extracts A, C (CORE_AC_EXTRACT) at 8am (996/12) |  |  | X |  | X |  |  |  | X
2021-07-16 |  | Run AP queries for unaccrued expenses >= $25K, provide to campus controllers for accrual consideration |  |  | X |  | X
2021-07-16 |  | 2nd Close (Period 996) Reports available on demand in the reporting system after 8am |  |  | X |  | X | X |  |  | X
2021-07-16 |  | CU Medicine to inquire against CIW for final Fund 80 FOPPS |  |  | X | [6 empty] | X
2021-07-16 |  | Campus deadline to record all Gift Revenue and Gift in Kind |  |  | X |  | X
2021-07-16 |  | COF and FFS Recon due to OUC from Budget |  | X |  |  | X
2021-07-16 |  | Known errors file update to OUC |  |  | X |  | X
2021-07-18 |  | Special run of FIN_WKNIGHT will occur including refresh at 6pm |  |  | X |  |  | X |  |  | X
2021-07-19 |  | 18th Avenue, LLC to provide June FINAL TB to OUC for blending & elimination entries |  | X |  |  | X
2021-07-19 |  | OUC will provide OPEB & AMP information to campuses to record in PeopleSoft |  |  | X |  | X
2021-07-19 |  | Inter/intracampus reconciliation of AR/AP for elimination entry (to be booked before 997 close) |  |  | X |  | X
2021-07-19 |  | Run Gift Journal - Fund-AUTOMIC: Gift_JRNL_FYE 5am (UIS to create) |  |  | X |  | X
2021-07-21 | 1 | FINAL CAMPUS CLOSE (Period 997) - All journals must be approved by 6pm |  | X | X | X | X | X | X | X | X | X
2021-07-21 | 2 | Last day to post manual accruals for all significant items by 6pm |  |  | X |  | X | X
2021-07-21 | 3 | Deadline for recording adjustments to investments, after this entries will not have allocations or PIE applied |  |  | X | X
2021-07-22 | 0 | USER ALERT : No journals should be approved or manually posted and no 998 entries should be created |  | X | X | X | X | X | X | X |  | X
2021-07-22 | 1 | Run 3rd close (Period 997) incremental allocations in Period 997 | [5 empty] | X |  |  | X
2021-07-22 | 1 | Run Revenue Reclass (RRCL process) | [5 empty] | X |  |  | X
2021-07-22 | 2 | Run Average Daily Balance (ADB) Monthly and Quarterly PIE | [5 empty] | X |  |  | X
2021-07-22 | 3 | Close Period 997 in PeopleSoft | [5 empty] | X |  |  | X
2021-07-22 | 4 | Open Period 998 after close completed |  |  | X |  |  | X
2021-07-22 | 4 | Add PIE System rates for Period 12 |  |  |  | X
2021-07-22 | 5 | Run budget-to-actual roll forwards |  |  | X |  |  | X |  |  | X
2021-07-22 | 6 | Transmit JVA1 file for 3rd June feed to CORE Period 12 by 6pm upon OUC approval |  |  | X |  | X |  |  |  | X
2021-07-22 | 7 | Run Detail PeopleSoft Extract & JVA1 file after FY2021 processing for 3rd June CORE feed (FINAL CORE Period 12) |  |  |  |  | X |  |  |  | X
2021-07-23 | 0 | USER ALERT : All unapproved FY2021 journals need to be reviewed by the campus controllers |  | X | X | X
2021-07-23 | 1 | Last day to have FY2021 MD and CR docs approved by State Treasury (treasurycashiers@state.co.us) |  |  | X |  | X
2021-07-23 | 1 | Run query for 6/30 ACC journals not marked to auto reverse & create reversal (dated 7/1) | [5 empty] | X |  |  | X
2021-07-23 | 2 | CORE FY2021 Period 12 close |  |  | X |  | X
2021-07-23 | 2 | Reminder that 998 entries should be adjusted for effect of allocation entries |  |  | X |  |  | X
2021-07-23 | 3 | Check CORE for feed errors |  |  |  |  | X
2021-07-23 | 4 | Run CORE Extracts A, C (CORE_AC_EXTRACT) at 8am (997/12) |  |  | X |  | X |  |  |  | X
2021-07-23 | 5 | Distribute detail CORE PeopleSoft Extract Report to campuses |  |  | X |  | X
2021-07-23 | 6 | Moratorium on new account requests ends (effective FY2022 only) |  |  | X |  | X
2021-07-23 | 6 | Moratorium on expense purpose code changes ends (effective FY2022 only) |  |  | X |  |  | X
2021-07-23 | 6 | Moratorium on Org tree changes ends (effective FY2022 only) |  |  | X |  |  | X
2021-07-23 |  | Bank statements due for completion of risk classification on Exhibit M |  |  | X |  | X
2021-07-23 |  | OSC will provide the allocation for posting Treasury Pooled Cash Unrealized Gain/Loss to institutions of higher ed, based on CORE's period 12 balances (CU Denver only for fund 333F entry) |  |  | X
2021-07-23 |  | Beginning this date, the exhibit reconciling balances will be available in InfoAdvantage for CORE Period 12 close balances. (Exhibit reconciling report is continuously available to run in InfoAdvantage) |  |  | X |  | X
2021-07-23 |  | Run AP queries for unaccrued expenses >= $25K, provide to campus controllers for accrual consideration |  |  | X |  | X
2021-07-23 |  | 3rd Close (Period 997) Reports available on demand in the reporting system after 8am |  |  | X |  |  | X |  |  | X
2021-07-23 |  | CU Denver campus PIE manual upload for new year |  |  | X
2021-07-23 |  | First day to change existing or request new allocations for July (FY2022) |  |  | X |  |  | X
2021-07-23 |  | Known errors file update to OUC |  |  | X |  | X
2021-07-26 |  | Update CORE open period to CORE Period 13 |  |  |  |  | X
2021-07-26 |  | For Fund 98 liabilities (AMP, OPEB, COMP ABS, PENSION) breakout Funds 1x for CORE 1100 & 1900 entries |  |  | X |  | X
2021-07-26 |  | CUPCO to provide June FINAL TB to OUC for elimination entries (Linda Money), no more entries to be booked |  |  |  | X | X
2021-07-26 |  | Altitude West to provide June FINAL TB to OUC for elimination entries (Teena Shepperson-Turner), no more entries to be booked |  |  |  | X | X
2021-07-26 |  | ULEHI to provide June FINAL TB to OUC |  |  | X |  | X
2021-07-26 |  | CUBEC to provide June FINAL TB to OUC |  |  | X |  | X
2021-07-27 |  | Review CORE extracts to balance due to/from and transfers |  |  | X |  | X
2021-07-28 | 1 | FINAL REVIEW BY CONTROLLERS - Last day for 998 entries |  |  | X |  | X
2021-07-28 | 1 | Transmit JVA1 file for Final FY2021 June feed to CORE Period 13 by 5pm upon OUC approval (period 998) |  |  |  |  | X |  |  |  | X
2021-07-28 | 2 | Period 998 closes at 3pm (only reopen with OUC approval) |  | X | X | x | X | X | X | X | X | X
2021-07-28 | 2 | Run Detail PeopleSoft Extract & JVA1 file after FY2021 processing for 998 June CORE feed (CORE Period 13) |  |  |  |  | X |  |  |  | X
2021-07-28 |  | Last day for State departments to direct bill with Higher Education via IET documents in CORE |  |  | X |  | X
2021-07-28 |  | After period 998 close, roll forward FY2021 ending balances to FY2022 beginning balances |  | X | X | x | X | X | X | X | X | X
2021-07-28 |  | After period 998 close, run cash rollup for CUPCO (funds 26, 72, 73, and 74) |  | X | X | x | X | X | X | X | X | X
2021-07-29 | 1 | Check CORE for feed errors |  |  |  |  | X
2021-07-29 | 2 | Run CORE Extracts A, C (CORE_AC_EXTRACT) at 8am (998/13) |  |  | X |  | X |  |  |  | X
2021-07-29 | 3 | Distribute detail CORE PeopleSoft Extract Report to campuses (last day to fix in PS to feed to CORE) |  |  | X |  | X
2021-07-30 |  | Known errors file update to OUC |  |  | X |  | X
2021-08-02 |  | Tobacco Cash Fund Certification due to State Treasury by noon (only applies to CU Denver) | 2021-07-22 |  | X
2021-08-02 |  | Marijuana Certification due to Department of Revenue by noon (only applies to CU Denver) | 2021-07-22 |  | X
2021-08-02 | 1 | Run query for 6/30 ACC journals posted in Period 998 not marked to auto reverse & create reversal (dated 7/1) |  |  |  |  | X | X
2021-08-02 | 2 | Create and roll forward the campus PIE rates |  |  | X |  |  | X |  |  | X
2021-08-02 | 3 | Set up monthly PIE journal page entry (FY2022) | [8 empty] | X
2021-08-02 |  | Last day to submit new allocation group requests for July (FY2022) |  |  | X
2021-08-02 |  | HR system upload of Faculty Contracts |  | X | X |  |  |  | X |  | X
2021-08-02 |  | External auditors to provide OUC with final Prepared By Client (PBC) list |  |  |  |  | X
2021-08-03 | 2 | Period 1 FY2022 closes for campus input at 6pm |  | X | X | x | X | X | X | X | X | X
2021-08-03 |  | Activate fixed amount allocations through Automic | [5 empty] | X |  |  | X
2021-08-04 |  | Do not feed Period 1 FY2022 to CORE until September |  |  |  |  | X |  |  |  | X
2021-08-04 |  | OUC to send warrants payable balance to Treasury (PBC C4) |  |  |  | X | X
2021-08-05 |  | Run Campus Exhibit J (JREC) files for Preliminary submission to OSC |  |  |  |  | X
2021-08-06 |  | Finalize State-funded student financial aid schedules (CDHE) and disclosures for external auditors |  |  |  |  | X
2021-08-06 |  | Known errors file update to OUC |  |  | X |  | X
2021-08-09 |  | Send Preliminary Exhibit J (JREC) to the Campuses for Variance Analysis and Expainations (due to David 8/23) |  |  | X |  | X
2021-08-12 | 1 | Final date for interface feeds to CORE (interface issues need to be corrected 8/13, extension granted from OSC for CU Medicine at end of August) | 2021-07-30 |  |  |  | X |  |  |  | X | X
2021-08-13 |  | Deadline to submit BGA90/91 documents for rollforward requests in the closing year to the OSC | 2021-07-30 |  | X
2021-08-13 | 1 | All transfers in CORE must be in balance by this date | 2021-07-22 |  | X |  | X
2021-08-13 | 1 | Deadline to clear all default and clearing accounts in CORE, including balance sheet account 159X | 2021-07-22 |  | X |  | X
2021-08-13 | 2 | Final day to revert remaining appropriation on expiring projects and/or process a carryforward on the valid portion of the project for which the department had encumbrances as of 6/30. Use the OSC-019 Capital Construction Reversions and Carryforwards Report to help identify expiring projects. | 2021-07-22 |  | X | X
2021-08-13 | 3 | Deadline for submitting appropriation transfer requests to the OSC (once approved by OSPB, departments will be contacted for BGA documents) | 2021-07-22 | X
2021-08-13 | 4 | CORE FY2021 Period 13 close. Documents processed after this date will route to OSC for approval after departmental approval | 2021-07-22 |  | X |  | X
2021-08-13 |  | State Treasury pool unrealized investment gains/losses must post to CORE by this date (only applies to CU Denver for fund 333F) | 2021-07-22 |  | X
2021-08-13 |  | Due date to submit Overexpenditure forms to the OSC | 2021-07-22 | X
2021-08-13 |  | Known errors file update to OUC |  |  | X |  | X
2021-08-14 |  | Perform preliminary review of the OSC-004 TABOR Nonexempt Revenue Variance report in infoAdvantage. No response to the OSC is required at this time. | 2021-07-22 |  | X |  | X
2021-08-14 |  | CORE FY2021 Period 14 open for input, subject to OSC approval | 2021-07-22 |  | X |  | X
2021-08-16 |  | OSC to provide IHE pension & OPEB liability calculation and sample disclosure (GASB 68 & GASB 75) within 5 business days of PERA's release of Pension Schedules | 2021-07-30 |  |  |  | X
2021-08-17 |  | Controller checklist due to OUC |  |  | X |  | X
2021-08-17 |  | TABOR Variance Analysis OSC-004 Report will be provided by OSC to each department in order to provide variance explanations | 2021-07-23 |  | X |  | X
2021-08-17 |  | All applicable exhibits (except J and K) due to OUC from campus, Treasury, and Budget | 2021-07-22 |  | X |  | X
2021-08-18 |  | CORE FY2021 Period 14 close | 2021-07-22 |  | X |  | X
2021-08-19 |  | CORE FY2021 Period 15 opens, subject to OSC approval | 2021-07-22 |  | X |  | X
2021-08-20 |  | State Receivable/Payable confirmation forms due to OSC | 2021-07-23 |  | X |  | X
2021-08-20 |  | CUPCO to provide final FY2021 financial statements and book any audit adjustments |  |  |  | X | X
2021-08-20 |  | Altitude West to provide final FY2021 financial statements and book any audit adjustments |  |  |  | X | X
2021-08-20 |  | ULEHI to provide draft FY2021 financial statements and book any audit adjustments |  |  | X |  | X
2021-08-20 |  | Officer Disclosure Information provided to Controller |  |  | X
2021-08-20 |  | Known errors file update to OUC |  |  | X |  | X
2021-08-23 |  | Preliminary Exhibit J (JREC) due from Campuses for consolidation |  |  | X |  | X
2021-08-23 |  | TABOR variance explanations (based on AS-TABOR report) due to the OSC | 2021-07-23 |  | X |  | X
2021-08-23 |  | Run AP queries for unaccrued expenses >= $25K, provide to campus controllers for accrual consideration |  |  | X |  | X
2021-08-24 |  | Exhibits due to OSC (excluding I, J, K, & CU Medicine) based on CORE's Period 14 balances | 2021-07-22 |  |  |  | X |  |  |  |  | X
2021-08-24 |  | ACFR Variance Analysis OSC-029 Report will be available to departments in infoAdvantage based on Period 14 ending balances | 2021-07-22 |  | X |  | X
2021-08-25 |  | Exhibit I due to the OSC |  |  |  |  | X
2021-08-25 |  | Consolidated financial statements due to OSC |  |  |  |  | X
2021-08-25 |  | Higher Education regular appropriated revenue and expense and informational only appropriated revenue and expense for budget reporting purposes (CORE model YE20) must be entered into CORE by this date |  |  |  |  | X
2021-08-25 |  | Preliminary Exhibit J (JREC) due to OSC |  |  | X |  | X
2021-08-25 |  | Materials deadline for RAC meeting (Q4 FY2021) |  |  |  |  | X
2021-08-25 |  | CU Medicine to provide CU Denver with final numbers & footnotes for recording in PeopleSoft |  |  | X | [6 empty] | X
2021-08-25 |  | Reopen Period 998 for CU Medicine entry and final campus accruals (re-close when posted) | [5 empty] | X |  |  | X | X
2021-08-25 |  | Update CORE open period to CORE Period 15 |  |  |  |  | X
2021-08-26 | 1 | 3pm deadline to approve and post CU Medicine & accrual JEs in PeopleSoft (final feed to CORE) |  |  | X |  | X |  |  |  |  | X
2021-08-26 | 2 | Run Detail PeopleSoft Extract & JVA1 file after FY2021 processing for Final 998 June CORE feed (CORE Period 15). Verify OUC Finance has posted all JEs. |  |  |  |  | X |  |  |  | X
2021-08-26 | 3 | Transmit JVA1 file for Final FY2021 June feed to CORE Period 15 by 5pm upon OUC approval (period 998) |  |  |  |  | X |  |  |  | X
2021-08-27 | 1 | Check CORE for feed errors |  |  |  |  | X
2021-08-27 | 2 | Run CORE Extracts A, C (CORE_AC_EXTRACT) at 8am (998/15) |  |  | X |  | X |  |  |  | X
2021-08-27 | 3 | Distribute detail CORE PeopleSoft Extract Report to campuses |  |  | X |  | X
2021-08-27 | 4 | Run Final Exhibit J (JREC) Campus files |  |  |  |  | X
2021-08-27 |  | Known errors file update to OUC |  |  | X |  | X
2021-08-27 |  | CU Medicine Exhibits due to OUC (C, D2, F1, F2, H, M, N1, N2, N3, T, W2) |  |  |  |  | X |  |  |  |  | X
2021-08-31 |  | SPA PIE interest earned transferred from Treasury to campuses posted to FY2022 |  |  | X | X
2021-08-31 |  | CUF to provide draft FY2021 financial statements (not notes)--send to OSC and external auditors |  |  |  |  | X
2021-09-01 |  | Due date for CORE's 4th Quarter report to OSC (based on period 14 balances) | 2021-07-23 |  | X |  | X
2021-09-01 |  | Exhibit J (JREC) sent by OUC to campuses to reconcile & provide explanations |  |  | X |  | X
2021-09-01 | 1 | Run query for 6/30 ACC journals posted in Period 998 not marked to auto reverse & create reversal (dated 8/1) | [5 empty] | X
2021-09-01 | 2 | Perform another rollforward of Period 0 balances (to capture effect of August 998 entries) | [5 empty] | X
2021-09-02 |  | Period 2 FY2022 closes for campus input at 6pm |  | X | X | x | X | X | X | X | X | X
2021-09-03 |  | ACFR Variance Analysis responses due to OSC | 2021-07-23 |  | X |  | X
2021-09-03 |  | Do not feed Period 2 FY2022 to CORE until end of September |  |  |  |  | X |  |  |  | X
2021-09-03 |  | All PBC items requested for final audit fieldwork due to OUC unless otherwise noted on PBC list |  | X | X | X | X |  | X
2021-09-03 |  | Footnote Template due to OUC from campus, Treasury, and Budget |  |  | X | X | X
2021-09-03 |  | YE Template due from PBA (2nd part) to OUC |  |  |  |  | X | X | X
2021-09-03 |  | CU Medicine to provide CU Denver with final audited FY2021 financial statements, CU Denver to send to OUC |  |  | X |  | X |  |  |  |  | X
2021-09-03 |  | Treasury will calculate pledged revenue for parenthetical disclosure & send to OUC |  |  |  | X | X
2021-09-06 |  | HOLIDAY |  | X | X | X | X | X | X | X | X | X
2021-09-07 |  | External auditors begin final fieldwork |  |  | X |  | X
2021-09-13 |  | CORE document catalog to be cleared of all FY2021 documents in draft or pending phase |  |  | X |  | X
2021-09-15 |  | Exhibit J (JREC) due to OUC for review & consolidation |  |  | X |  | X
2021-09-16 |  | Subsequent events reporting related to the basic financial statements is due to OSC |  |  |  |  | X
2021-09-16 |  | UBIT final actuals for fiscal year ending 6/30/2021 due to Tax Director |  |  | X | X
2021-09-17 |  | Exhibit J (JREC), draft footnotes, and MD&A due to OSC |  |  |  |  | X
2021-09-20 | 1 | CORE FY2021 Period 15 close |  |  | X |  | X
2021-09-20 | 2 | Statutory deadline for issuing the State's FY2021 basic financial statements |  |  |  |  | X
2021-09-20 |  | CORE Clear (Period 1 FY2022) |  |  |  |  | X |  |  |  | X
2021-09-21 |  | Transmit JVA1 file for July feed to CORE (Period 1 FY2022) upon approval by OUC |  |  |  |  | X |  |  |  | X
2021-09-22 |  | CORE Clear (Period 2 FY2022) |  |  |  |  | X |  |  |  | X
2021-09-23 |  | Transmit JVA1 file for August feed to CORE (Period 2 FY2022) upon approval by OUC |  |  |  |  | X |  |  |  | X
2021-09-24 |  | ULEHI to provide final audited FY2021 financial statements |  |  |  |  | X
2021-09-30 |  | Create copies of all GASB Tables, rename as FY2022 version |  |  |  |  | X |  |  |  | X
2021-09-30 |  | UBIT estimates for 1st quarter ending 9/30/2021 due to Tax Director |  |  | X | X
2021-09-30 |  | Exhibit K1 due to OUC for review |  |  | X |  | X
2021-09-30 |  | CORE Clear (Period 3 FY2022) |  |  |  |  | X |  |  |  | X
2021-10-01 | 1 | CUF to provide 2nd draft FY2021 financial statements (with notes)
2021-10-01 | 2 | Send CUF's second draft financial statements to OSC (and external auditors) |  |  |  |  | X
2021-10-01 |  | Mandatory Fiscal Certification closes to general population |  |  | X |  |  | X
2021-10-01 |  | Request President's Letter for Annual Financial Report (AFR) |  |  |  |  | X
2021-10-01 |  | Report Template due from Budget (Chad Marturano) to OUC |  | X |  |  | X
2021-10-01 |  | Exhibit K1 due to OSC and BKD |  |  |  |  | X
2021-10-05 |  | Transmit JVA1 file for September feed to CORE (Period 3 FY2022) upon approval by OUC |  |  |  |  | X |  |  |  | X
2021-10-08 | 1 | Fiscal Certification application closes for the year |  |  | X |  |  | X
2021-10-08 | 2 | University Controller completes the Fiscal Certification |  |  | X |  |  | X
2021-10-15 |  | Audited financial statements from DPCU meeting the materiality threshold due to the OSC |  |  |  |  | X
2021-10-22 |  | CUF to provide final audited FY2021 financial statements--send to OSC and external auditors |  |  |  |  | X
2021-10-22 |  | Copy of external auditors' management representation letter due to OSC and OSA (when available) |  |  |  |  | X
2021-10-29 |  | Due date for Q1 quarterly report to OSC |  |  | X |  | X
2021-11-01 |  | Final Exhibit J (if changes made since 9/17) and Final Annual Report due to OSC prior to release (when available) |  |  | X |  | X
2021-11-05 |  | Controller Checklist Part E due to OUC |  |  | X |  | X
2021-11-10 |  | Exit conference (tentative date only) |  |  | X |  | X
2021-11-15 |  | External auditors' deadline to issue report to OSA |  |  |  |  | X
2021-11-24 |  | Materials deadline for RAC meeting (Q1 FY2022) |  |  |  |  | X
2021-12-03 |  | OSA's management representation letter due to OSC and OSA (when available) |  |  |  |  | X
2021-12-06 |  | Legislative Audit Committee (LAC) meeting |  |  |  |  | X
2021-12-08 |  | Regent Audit Committee (RAC) meeting |  |  | X |  | X
2021-12-10 |  | External auditors to provide PDF and printed copies of OSA report & management letter & 3 copies to OSA |  |  | X |  | X
2021-12-17 |  | Subsequent events reporting related to the ACFR is due to the OSC |  |  |  |  | X
2021-12-17 |  | CORE FY2021 Period 16 close - ACFR and audit opinion issued |  |  | X |  | X
2021-12-31 |  | Submit Financial Responsibility and Accountability Act Statements to OSC (12/31 deadline for FRAC) |  |  |  |  | X