## Portfolio Overview
Cross Campus Collaboration (C3) Leadership Project Portfolio Overview | [17 empty] | June 2021
Projects in Planning, Executing, or Closing Phase (2, 3, or 4) | [7 empty] | Project Health |  |  | % Comp |  | Schedule - Calendar Year
Name | FY20 Priority | Phase | Sponsor | Start Date | Size | C3 Sponsor | Primary | Schedule | Cost | Scope | Last | Now | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22
Cloud Enablement and Foundation Services - Initiation and Solution Design Phase | 3.2 Establish Communities of Practice and a Culture of "One IT" Across CU | @3 | C3 | 2021-04-01 | L | Greg Williams, Sheard Goodwin, Tony Brooks, Orrie Gartner | Barb Schnell, Jason Armbruster | Green | Green | Green | 5% | 10%
GitHub Enterprise | 4.8 Rationalize Common Applications to Reduce Redundancy | @3 | C3 | 2021-05-01 | S | Orrie Gartner | Todd Schaefer | Green | Green | Green | 0% | 20%
Messaging and Collaboration Enablement and Optimization | 4.8 Rationalize Common Applications to Reduce Redundancy | @3 | C3 | 2020-11-01 | L | Jill Ibeck | Kerry Havens | Yellow | Green | Green | 20% | 20%
Projects in Initiating Phase (1A or 1B) | [12 empty] | Schedule Estimate - Calendar Year
Name | FY19 Priority | Phase | Sponsor | Date | C3 Sponsor | Primary | Notes | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Identity and Access Management Enablement and Optimization | 4.4 Implement an Enterprise Identity and Access Management Approach Across CU | 1B | CIOs | 2021-01-01 | Jill Ibeck | Kerry Havens | Project charter developed. Awaiting next steps.
Network Enablement | 4.2 Enhance Networking Capabilities Acrosss CU and Improve Wi-Fi Services | 1B | C3 | 2021-01-01 | Sheard Goodwin | Piotr Artwich | Summary state being developed along with charter to develop standing committee
Future Projects/Ideas (Phase 0)
Name | FY19 Priority | Phase | Requestor | Date | Primary |  |  | Notes
Completed Projects
Name | FY20 Priority | Phase | Requestor | Date | Sponsor |  |  | Notes
Teams VoIP POC | 4.8 Rationalize Common Applications to Reduce Redundancy | 4 | CU Denver | 2020-02-01 | Sheard Goodwin |  |  | Explore the use of Microsoft TEAMS for voice as a possible replacement for other telephony options such as older analog systems, or Cisco VoIP.
CUNet Current Status Report | 4.2 Enhance Networking Capabilities Acrosss CU and Improve Wi-Fi Services | 4 | C3 | 2020-02-01 | Orrie Gartner |  |  | CUNet current state report completed
Learning Collaboration Tool RFP | 4.8 Rationalize Common Applications to Reduce Redundancy | 4 | CIOs | 2020-05-01 | Orrie Gartner |  |  | what are the right learning tool or tools for collaboration? Zoom was chosen and implemented.
Note on E7: orrie: Date approved by C3

## Template
Cross Campus Collaboration (C3) Leadership Project Portfolio Overview | [17 empty] | January 2021
Projects in Planning, Executing, or Closing Phase (2, 3, or 4) | [7 empty] | Project Health |  |  | % Comp |  | Schedule - Calendar Year
Name | FY20 Priority | Phase | Sponsor | Start Date | Size | C3 Sponsor | Primary | Schedule | Cost | Scope | Last | Now | #REF! | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22
Projects in Initiating Phase (1A or 1B) | [12 empty] | Schedule Estimate - Calendar Year
Name | FY19 Priority | Phase | Sponsor | Date | C3 Sponsor | Primary | Notes | [5 empty] | #REF! | 0 | 0 | 0 | 0 | 0
Future Projects/Ideas (Phase 0)
Name | FY19 Priority | Phase | Requestor | Date | Primary |  |  | Notes
Completed Projects
Name | FY20 Priority | Phase | Requestor | Date | Sponsor |  |  | Notes

## Chart Data
This tab populates the calendar information on the rest of the spreadsheet. Updating a yellow field will change the data on each tab. | [10 empty] | TIP Initiatives
1.1 Redefine the Role of IT across CU to Clarify Responsibilities
|  | Schedule Fields | [8 empty] | 1.2 Enhance System IT Governance to Improve Collaboration and Efficiency
Report Month | June 2021 | % | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 |  |  | 2.1 Redesign IT Funding Models to Improve Services and Reduce Duplication
2.2 Establish Standards and Processes to Support More Effective and Efficient Procurement of IT
3.1 Rationalize IT Organizational Structure and Job Titles
3.2 Establish Communities of Practice and a Culture of "One IT" Across CU
4.1 Consolidate Data Center Infrastructure Across CU and Standardize Cloud Capabilities
To update the chevron diagram, click on the graphic below, then edit the text in the left box. Then image capture the chevrons and paste into each tab | [10 empty] | 4.2 Enhance Networking Capabilities Acrosss CU and Improve Wi-Fi Services
4.3 Enhance High Performance Computing Capabilities to Advance Research and Innovation
4.4 Implement an Enterprise Identity and Access Management Approach Across CU
4.5 Develop an Enterprise Approach to Security Operations
4.6 Deploy a Common Integration Layer to Enable Data Sharing Across CU
4.7 Develop a CU-Wide CRM Strategy for Most Common Use Cases
4.8 Rationalize Common Applications to Reduce Redundancy
5.1 Implement Enterprise IT Asset Management Processes and Tools to Reduce Risk Profile
5.2 Accelerate Adoption of Standardized ITSM Processes, Service Catalogs, and SLAs to Improve the Customer Experience
6.1 Define a CU-wide Data Strategy to Improve Access to Data and Standardized Reporting
6.2 Support Student Success at CU and Collaborate on Shared Needs and Best Practices
6.3 Launch a Multi-Disciplinary IT Innovation Hub Responsible for the Implemenation of Next-Generation Technology at CU
[9 empty] | = Confirmed schedule. | = Schedule estimate only. Final schedule still TBD