## Issues
Item | Priority | Submitted By | Category | Issue Description | Examples Provided | Status | Comments | Resolution | Date
20 | 1-FYE | Newsome, Linda, Boulder | GL - Cash Roll-up | Cash rollup speedtypes still need to be added to new fund 12 cost share | See a tab "School Cash Roll-up-Fnd 12" | In development | All are caught up, development is underway for allowing cross-fund online. | All were uploaded prior to February close. 61200001 was created online on 1/25 without that entered, please update online. Is Quarterly PIE including new cost share funds.
25 | 1 | Coming, Marilyn | GL - Security | Budget office personnel does not have access to Chartfields Attributes | See Excel Tab titled "Chartfield Attributes" | In development | Query is work around until link is opened on display only page. | Must use query since display only pages do not have any field including links active. | WAIT as of 5/20 meeting
29 | 1 | Boulder | GL | SpeedType missing from Ledger line (and Journal line) |  | Investigating | Provide examples if not resolved | Cal thought these should be synced up. Does this still need to be open?
35 | 2 | Shagdar, Nara | CIW | Few programs and projects listed twice in ARTEMIS_GL_SPEEDTYPE_LOOKUP_TBL. It looks like if BU is UCOLO, then speedtype is blank. | See a tab "No speedtypes" | In development | Related to issue 1
36 | 3 | Yu, Ryan | GL - JE Delete | Hard for users to delete a JE (restrictions such as all lines must be valid without error) |  | In development
37 | 2 | Yu, Ryan | GL - Chartfield | There is no function on Fin 9.2's Chartfield to check Fund/ Account Code combo. |  | In development | Custom fund/account pages are being brought back. | Checking with Kieth Carpenter on Status Update | 2016-04-30
38 | 2 | Yu, Ryan | Fin - Student Loan | There has been no student loan transaction feeds since 12/31/2015 (partly due to new loan servicer). |  | In development | Campus partners is no longer the provider of this information and a new project is started with Heartland ECSI | Heartland File Sent 05/25/2016 | 2016-05-15
39 | 2 | Boulder | Workflow | Access to change public query. |  | In Testing | Production access will not be expanded, access in non-prod will be given for migration by System admin after Phire workflow is implemented.
40 | 3 | Boulder | GL | Need a customization for re-orgs |  | In development | Retrofitting 8.4 custom | Push to FY 2017
43 | 2 | Yu, Ryan / Acierno, Ginger | GL- Clearing Account Codes | Six projects carry clearing account balances ($360K total) in error | See Attached | Open
44 | 1-FYE | Yu, Ryan | GL - Cash Roll-up | Cash Roll-up - 26 speedtypes (UPI’s Fund 80) - $267K cash total after January close. It should have been rolled into the UPI’s cash pool speedtype | See Attached | Open | Ryan Yu to verify - wait. 05/26/16 - Ryan Yu ran Report and still has Speet Types in Error on his Query List.
46 | 2 | Thomas, Johnston | PSAM | Spreadsheet loader problem. We have three months data for equipment and library purchases plus other items to upload to PSAM, around 300 lines. Also, we have about a backlog of 200+ new tags that need to be affixed but it's on-hold currently. | Cal already has it | In Testing | Currently works if PI # is included
48 | 2 | Shagdar, Nara | Security | I cannot approve journal from "Work list". | See Attached | Open | we haeve a workaround - wait
49 | 1 | Yu, Ryan | GL - Security | Kelly Mcllvride, CU Denver's accountant responsible for reviewing JEs, still doesn't have access to her worklist. |  | Open
50 | 2 | Yu, Ryan | GL - Worklist | Worklist is still listing JEs which have been posted in January. (See YUXX000114's worklist, TRY001-015 still listed) |  | Open
51 | 1 | Yu, Ryan | GL - Workflow | Workflow for JEs created by the Finance Office's sourece code is still not right. They should not be routed to Office of Grants and Contracts. | JE0001182124 | Open | So even if fund 30/31, they should not route to OGC? |  | WAIT as of 5/20 meeting
52 | 2 | Yu, Ryan | GL - Workflow | JEs without any workflow stop should be but have not been defaulted to UCD Controller stop. | JE0001176506 | Open
53 | 2 | Yu, Ryan | GL - Workflow | UCD Finance's accountants still have their JE approver role in wrong workflow stop. |  | Open | Need details
55 | 2 | Yu, Ryan | CIW - GL_PROJECT_TBL | Missing project expense purpose code field. | Sample file C7 - Excel Tab | In development | m-FIN reports use GL_PROJ CIW will accommodate by also adding EPC to GL_PROJECT_TBL
56 | 2 | Yu, Ryan | CIW - GL_PROJECT_TBL | No data in expense purpose code description field | Sample file C8 - Excel Tab | In development | m-FIN reports use GL_PROJ CIW will accommodate by also adding EPC to GL_PROJECT_TBL
57 | 2 | Coming, Marilyn | GL - Journal Lines | Budget journal lines have FTE identified. Printed journal doesn't include. | See Attached | In Development | Need to know if columns can work instead of a special line
58 | 1 | Coming, Marilyn | GL - Journal Lines | When selecting Ledger types in Journal Lines, all campus users have B_INI_ ledger available. This should only be available to Budget Office. |  | Phase 2 | Workflow currently prevents posting unwanted journals. Will explore ledger security which was not implemented at go-live | No update as of 05/26
62 | 1 | Boulder | GL | Need access to gift attributes page for fund 32 speedtypes |  | In development | Jonathan is devloping with Rob Lucas testing
64 | 1 | Boulder / UCCS / UCD | Workflow | Don't have the ability to click buttons for "Mark Worked" and "Reassign" |  | Don't have the ability to click buttons for "Mark Worked" and "Reassign" | In development | Cleanup script of worked items being created. Setting on server being tested.
67 | 2 | UCCS | GL-Security | Carolyn Rupp does not have User Role access anymore |  | In development | Security is updating basic FIN security to view page
72 | 1 | UCCS | AR | No matching value for the invoice Item ID when trying to apply payments on invoices created post go |  | Open | Cerelia researching Cash Application issues
78 | 1 | Boulder | Reports | Several departments were interested in the capability of nVision to streamline reporting within their departments (CIRES) |  | In development | New security role
79 | 1 | Boulder | GL | Departments would like to receive notifications when their uploads are successful/not, so they can easily monitor the status |  | Open | Black box feeds | Talk to prod services
80 | 2 | Boulder | Projects | Utilizing project costing for dept. needs - Depts Include: LASP, Engineeering, CIRES |  | Phase 2
83 | 1 |  |  | Need a cash transfer journal customization to help automate cash transfer validation using the cash transfer matrix rather than manual approval by campuses. |  | New | Move from Critical to High. Does not need to be FYE. Linda Warren thinks we can use People Code. Address after FYE.
84 | 1 |  |  | ID account codes should balance on journals |  | New | Higher priority than item 83. After FYE
92 | 1-FYE | Accounting Services | Queries | Need help with 55 queries for auditors/ foundation/ reconciliation - 18 unable to locate in 9.2 - Period 1-9 and 10-12 Expense Population for Auditors - 37 producing inaccurate results |  | In development | Queries devided between Ryan & Rob, may look outside for additional resources. Jane is reviewing the latest Expense Pop Results.
97 | 2 | Accounting Services | GL Reconciliation | Access to Cash Management (for David & Brent) in order to see ACH rejects and returns detail |  | Investigating | 4/25 David to sit with Shannon to get screen shots of Cash Management module needed, then Cal will grant read-only access to those areas
98 | 1-FYE | Accounting Services | GL Reconciliation | Reconciliation for Payroll and BRS warrants (similar to AP automated process)… Have been unable to reconcile Payroll Warrants since go-live. |  | In development |  | Lisa Affleck / Peggy Watson - still working on this issue
99 | 3 | Accounting Services | GL Reconciliation | JE AP01143123 has two voids with no voucher $27.46 & $35.02 (old issue, not FIN 9.2 related) |  | Investigating
101 | 3 | Accounting Services | GL | Account/Fund combo not in 9.2 (needed by Jane & Brent when setting up new accounts) |  | Delete | Duplicate Issue of 37
103 | 1-FYE | Accounting Services | Access | Need access to GASB Accounts and GASB Codes in 9.2 (Jane & Brent) |  | In development | Ryan approved Security role being updated on 5/26. Access team to complete.
104 | 3 | Accounting Services | Reports | Trial Balance in FIN (shows beginning balance, current activity, ending balance) |  | Investigating | David working with Carl
106 | 1-FYE |  | Asset Management | Depreciation reporting tables. |  |  | Ryan Day working on this with Linda and Greg - unique contraint error when attempting to build the historical tables
107 | 1-FYE | Accounting Services | GL / Cognos Reporting | Program / Projects Budget Roll Forward |  | In development | Bring back 8.4 SQRs - Submitted to UIS 05/26/2016

## Closed Issues
Items | Priority | Submitted By | Category | Issue Description | Examples Provided | Status | Comments | Resolution | Date
2 | 1 | Coming, Marilyn | GL - Auxiliary | Auto posting of Budget Journal from Auxiliary budget panel. These journals should post overnight and are in Journal Status T. All are under Source DBO |  | Closed |  | Issue resolved. Program fixed to assign status N instead of T.
3 | 1 | OGC | Invoicing | Invoicing - VA billing |  | Closed | Grants issues are tracked separately
16 | 2 | Thomas, Johnston | PSAM | The updates show in PSAM but the CIW Responsible Person table still shows the old data/person for the records. | Tag#106229 - Old RP ID 217549 and new RP ID 258379 | Closed |  | New CIW table is AM_ASSET_RESP instead of AM_ASSET_RESP_CU
17 | 1 | Roche, Diane | GL - PIE Reports | No access to PIE reports yet. | No | Closed |  | Role CU GL Campus Manager does have this access
18 | 1 | Yamashita, Brett/Shagdar, Nara | GL - Allocation | View table referencing a wrong table for HCNST/3A, 8A, 9A and no journals created | See Attached | Closed | Journals did create for February close | View fixed
19 | 1 | Yamashita, Brett | Security | Both Brett Yamashita and Khalid Amboka cannot update Project_Team | See Attached | Closed | Project fiscal manager needs to be role GADM, not the project manager checkbox
21 | 1 | Yu, Ryan | GL - Workflow | JEs with lines only involving Fund 35 have been automatically posted with any workflow. | JE0001176506 | Closed |  | Rule fixed. Was initially created for program code not equal blank. That was incorrect for funds 32 and 35 which are project
22 | 2 | Yu, Ryan | GL - PS Query | Fin 8.4 PS queries/reports have not been fully converted to Fin 9.2. |  | Closed
23 | 2 | Yu, Ryan | GL - CU SIS Feeds | CU SIS feeds to GL have not been on time. Sometimes, a week's or twe-week feeds were batched together. |  | Closed |  | All journals retain their accounting date assigned in CU-SIS. Custom process to mark to post has been implemented
24 | 2 | Yu, Ryan | CIW - GL_SPO_ENCUMB_LINES_BASE | No data in this table |  | Closed |  | This was not brought forward since we no longer have SPOs separate from Pos.
26 | 1 | Boulder | GL Allocations | LOC allocations will not validate and it has something to do with foreign currency code |  | Closed | Journals posted properly for February close
27 | 1 | Boulder | GL Allocations | 1B-CHEM allocation group not producing journal at Close |  | Closed | Journals posted properly for February close
28 | 1 | Boulder | GL | It looks like many pre-approved journals are not posting at this time (Blackbox and Bursars Feed are examples) |  | Closed
30 | 1 | UCCS | GL-JE's | Need Edit checks in JE's: if inactive ST, wrong FOPP in upload-there should be an error |  | Closed | Edit check works for online. Journal upload also gives error if ST is inactive. Upload spreadsheet does not do combo edit, just field validation. Feeds from HCM, CU-SIS, Concur are overridden
31 | 2 | UCCS | GL-JE's | Search for JE's using "begins with" for the source code |  | Closed | Use In List instead and save a search criteria
34 | 1 | Yamashita, Brett/Nara Shagdar | GL - Allocation | Fringe benefit allocations for the pay end date prior to Dec 1 is still not generating journals. | See Attached | Closed |  | For pay end date, both from and to value must be defined on the range
41 | 1 | UCCS | Billing | Unable to update sponsor addresses |  | Closed |  | Security updated for customer maintenance role | 2016-04-19
45 | 2 | Yu, Ryan / Acierno, Ginger | GL - EPC | No EPC in CIW tables or PSC chart field on several projects. EPC is on the award. For any new setups, where the letter is the 3rd digit of the project, EPC is not on the project attribute. | See Attached | Closed |  | Projects with missing attribute have been updated
47 | 2 | Thomas, Johnston | PSAM | Cannot update Custodian in PSAM. | See Attached | Closed |  | Fix to bypass default workflow migrated on 4/14 | 2016-04-14
59 | 1 | Nguyen, Lien | GL - Query | a problem with the view when adding the controller defined field criteria "PF" to the CU_PROGRAM_VW. | see attached | Resolved |  | 49 programs had all historic values for the controller defined converted instead of just the most recent were causing the problem. The newest value from 8.4 was kept and the others are being deleted
71 | 2 | UCCS | AM | An extra January depreciation for fixed assets |  | Closed | There is no extra depreciation. There is only 1 depreciation journal per accounting period. | After running December depreciation and closing the month, I noticed October and November depreciation was never run. I ran these months for you in January causing 3 journals: one for October, one for November, and one for January.
74 | 1 | UCCS | GL-JE | Our cashier over/short account is no longer posting to the GL for some reason, it shows a FUND/ ACCT error on the JE. |  | Closed | Need the account and fund detail | The journals with this error were actually FOPPS error instead of fund/account. Journals after 3/9 post fine. 3 journals went to suspense from CU-SIS 3/9 and earlier and should be corrected via suspense correction.
77 | 1 | UCCS | Assets | PSAM month end closing - many things have changed on screens, options - we need new training or guides to be able to do it right. Right now, we are relying on Cal to do it for us. We can enter new assets, retire, adjustments, but lost at the month-end processes. |  | Closed |  | Updated the documents and sent.
82 | 2 |  |  | F&A account description is misleading to say off-campus |  | Closed | Accounting Services updated the description
76 | 1 | UCCS | Query | NET BOOK VALUE query is not working, and there are no reports in Cognos for it. Auditors go by it for assets |  | Closed | No query | These public queries are back: AM_NBV_CU - Asset Net Book Value AM_ASSET_NBV_CU - Asset Net Book Value AM_DEPR_CLOSE_CU - Monthly Depreciation Expense AM_ADDITIONS_CU - Asset Additions AM_JOURNAL_DETAIL - Asset Details for a Journal AM_RETIREMENTS_CU - Asset Retirements
6 | 1 | Boulder | Workflow | Any time a Boulder journal hits any Denver ST that journal enters not only Boulder’s approval workflow, but also Denver’s workflow. |  | Closed |  | No new issues reported
1 | 1 | Yu, Ryan | GL - JE Edit check | Fin 9.2’s JE edit check doesn’t check on PC Business Unit for programs | See Attached | Closed | No journals after 1/31/16 have posted this way. Because pc BU is not a ledger field, we will delete PC BU and activity ID from those past journals.
42 | 1 | Yu, Ryan | GL - Cash Roll-up | Cash line allocation did not process pursuant to a JE correcting entry | See Attached | Closed |  |  | 2016-04-30
68 | 1 | UCCS | GL-Allocation | Problems updating our allocations |  | Closed | Need specific steps giving problems.
85 | 1 |  |  | Reporting security for Assets |  | Closed | CU AM Asset Accountant has all known access.
94 | 1 | Accounting Services | GL Financials | SNP and SRECNP out of balance by $26.75 in Nov statements caused by one-sided entry |  | Closed
96 | 1 | Accounting Services | GL Financials | Unassigned balance in restricted fund discovered in UCD's February statements, due to about 275 projects without EPC in CIW's project table |  | Closed
102 | 3 | Accounting Services | Access | Need access to ACCT_ROLLUP_CU in 9.2 (Jane & Brent) |  | Closed |  | Resolved when all campus tree access issues were resolved
66 | 1-FYE | UCCS | Workflow | Charles David Moon and Brad Bayer cannot approve JE's from their worklist |  | Closed |  | For Charles Moon, the permission list was missing from his workflow role CU WF Journal UCCS VCAA For Brad Bayer, his workflow had not yet been created.
100 | 1-FYE | Accounting Services | GL Year End | Year-end procedures for Pay Date Shift & Payroll Accrual needed in FIN9.2 similar to FIN8.4 | Closed | In development |  | Testing completed by Brent 1/16
73 | 1 | UCCS | Fin Aid Projects | Fund 30 revenue reclass process | Closed | Complete |  | The campuses will handle the
54 | 1 | Yu, Ryan | GL - PS Query | Need a PS query to provide information of JE workflow progress. |  | Cancelled | Duplicate of Item 75 | Try query CU_GL_WORKFLOW_STATUS_TRACK
61 | 1 | Boulder | Workflow | Maggie needs access to change workflow. |  | Cancelled
63 | 1 | Boulder | Workflow | Worklist does not clear for approved items |  | Complete | In Testing | Intermittent for some users.
75 | 1 | UCCS | GL-Workflow | Need a query to see workflow, CU_GLJOURNALAPPROVAL_WRKFLWDEF, not working |  | Resolved | Need confirmation that this new query is working as a substitute. | Try query CU_GL_WORKFLOW_STATUS_TRACK | 2016-04-15
81 | 2 | Boulder | GL | Budget account codes should only be used with the budget ledgers. |  | Closed
95 | 1 | Accounting Services | GL Financials | SNP and SRECNP out of balance by $4,606 in Dec statements is caused by cash line allocation on approx 10 FOPPS (UCD) |  | Closed | CLOSED - 94&95
70 | 2 | UCCS | GL-Reporting | Fund XY showing up on GASB statements |  | Closed
65 | 2 | Boulder | Workflow | When add a line, it doesn't change the amount to a negative amount |  | Closed | Intermittent for some users. | Our primary permission lists prior to business unit security had entry and line copy templates that were not recreated on those lists. The templates themselves have now been updated to not create amount which actually does copy down opposite sign.

## No Speedtypes
SPD_KEY_CODE | ARTEMIS_GL_SPEEDTYPE_LOOKUP_TBL.PROJ_ID | ARTEMIS_GL_SPEEDTYPE_LOOKUP_TBL.PGM_CODE | Example: Proj 3535733
| 2039950 |  | BUSINESS_UNIT | FUND_CODE | FUND_DESC | DEPT_ID | DEPT_DESC | PGM_CODE | PGM_DESC | BUSINESS_UNIT_PC | PROJ_ID | ACTIVITY_ID | PROJ_DESC | SUBCLASS_CODE | SUBCLASS_DESC | SPD_KEY_CODE | SPD_DESC | SPD_LOOKUP_EXTRACT_AS_OF_DATE
| 3535879 |  | UCOLO | 30 | SPONSORED PROJECTS- FED & PRIV | 30074 | CEAS-ELECTRICAL ENGINEERING |  |  | UCD | 3535733 | 1 | TSGTA STATE ESTIMATION |  |  | 63007989 | TSGTA STATE ESTIMATION | 2016-03-16 22:20
| 3535733 |  | UCOLO | 30 | SPONSORED PROJECTS- FED & PRIV | 30074 | CEAS-ELECTRICAL ENGINEERING |  |  | UCOLO | 3535733 | 1 | TSGTA STATE ESTIMATION |  |  |  |  | 2016-03-16 22:20
22302
49016
25M1000
2050056
19051
51869
3640953
21839
| 2539967 | [10 empty] | 2039950
| 2582731 | [10 empty] | 3535879
|  | 60605 | [9 empty] | 3535733
| 2517851 | [10 empty] | 25M1000
| 2510358 | [10 empty] | 2050056
| 2539999 | [10 empty] | 3640953
| 2512235 | [10 empty] | 2539967
| 2517845 | [10 empty] | 2582731
|  | 60150 | [9 empty] | 2517851
| 2301163 | [10 empty] | 2510358
| 2050055 | [10 empty] | 2539999
|  | 22294 | [9 empty] | 2512235
|  | 53367 | [9 empty] | 2517845
|  | 41715 | [9 empty] | 2301163
|  | 39011 | [9 empty] | 2050055
| 2581932 | [10 empty] | 2581932
|  | 39942 | [9 empty] | 2552872
| 2552872 | [10 empty] | 2574832
| 2574832 | [10 empty] | 2515968
2515968

## School Cash Roll-up Fnd 12
SpeedType | *Effective Status | Description | Organization | Fund Code | Program Code | Project | Sub-Class | Pooled Investment Earnings | Cash Rollup SpeedType | Foundation Fund | Gift Purpose Code 1 | Gift Purpose Code 2
61200001 | Active | COST SHARE FOR 3535911 | 30077 | 12 | (blank) | 35M1000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200002 | Active | Cost Share for 3535147 Gibson | 60087 | 12 | (blank) | 3535147 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200004 | Active | Cost Share for 2552667 Bayer | 60087 | 12 | (blank) | 2552667 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200005 | Active | Cost Share for 2522384 Duncan | 60087 | 12 | (blank) | 2522384 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200006 | Active | Cost Share for 2510195 Ford | 60087 | 12 | (blank) | 2510195 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200007 | Active | Cost Share for 2513114 Ford | 60087 | 12 | (blank) | 2513114 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200157 | Active | CF Cost Share for 3535774 | 30074 | 12 | (blank) | 3535774 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200180 | Active | Cost Share for 2522648 | 60087 | 12 | (blank) | 2522648 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200185 | Active | CF COST SHARE FOR 2581368 | 20985 | 12 | (blank) | 2581368 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200244 | Active | CF COST SHARE FOR 2574496 | 20985 | 12 | (blank) | 2574496 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200247 | Active | CF Cost Share for 3535277 | 30110 | 12 | (blank) | 3535277 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200375 | Active | Cost Share D for 2524111 | 30071 | 12 | (blank) | 2524111 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200378 | Active | CF COST SHARE FOR 2522921 HILD | 20868 | 12 | (blank) | 2522921 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200379 | Active | CF COST SHARE FOR 2522921 COEC | 20868 | 12 | (blank) | 2522921 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200437 | Active | Cost Share for 3535337 Gibson | 60087 | 12 | (blank) | 3535337 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200439 | Active | CF COST SHARE FOR 2581575 | 20985 | 12 | (blank) | 2581575 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200444 | Active | CF COST SHARE FOR 2574629 | 20985 | 12 | (blank) | 2574629 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200448 | Active | CF COST SHARE FOR 2510246 FORD | 20249 | 12 | (blank) | 2510246 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200452 | Active | Cost Share for 2511257 | 20173 | 12 | (blank) | 2511257 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200453 | Active | CF COST SHARE FOR 2511257 | 20169 | 12 | (blank) | 2511257 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200464 | Active | CF COST SHARE FOR 2510245 | 21577 | 12 | (blank) | 2510245 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200544 | Active | Cost Share for 2552778 | 60087 | 12 | (blank) | 2552778 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200554 | Active | Cost Share for 2590284 | 60087 | 12 | (blank) | 2590284 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200621 | Active | Cost Share for 2523175 Johnson | 60087 | 12 | (blank) | 2523175 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200683 | Active | CF COST SHARE FOR 2574745 | 20985 | 12 | (blank) | 2574745 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200705 | Active | CF COST SHARE FOR 2581847 | 20985 | 12 | (blank) | 2581847 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200753 | Active | CF COST SHARE FOR 2581859 | 20269 | 12 | (blank) | 2581859 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200933 | Active | CF COST SHARE FOR 2582035 | 20985 | 12 | (blank) | 2582035 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200942 | Active | CF COST SHARE FOR 2510299 | 21379 | 12 | (blank) | 2510299 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61200959 | Active | CF COST SHARE FOR 2570183 | 20138 | 12 | (blank) | 2570183 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201037 | Active | Cost Share for 3535598 | 30124 | 12 | (blank) | 3535598 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201098 | Active | CF Cost Share for 3535739 | 30108 | 12 | (blank) | 3535739 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201132 | Active | Cost Share for 2510245 | 20105 | 12 | (blank) | 2510245 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201139 | Active | Cost share for 2591055 | 20109 | 12 | (blank) | 2591055 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201146 | Active | Cost Share for 3535638 | 30087 | 12 | (blank) | 3535638 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201307 | Active | Cost Share for 2582332 | 20985 | 12 | (blank) | 2582332 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201364 | Active | Cost Share B for 2524111 | 20127 | 12 | (blank) | 2524111 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201365 | Active | Cost Share C for 2524111 | 20335 | 12 | (blank) | 2524111 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61201470 | Active | Cost Share B for 2590359 | 20112 | 12 | (blank) | 2590359 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209244 | Active | Cost Share for 2574496 | 20985 | 12 | (blank) | 2574496 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209247 | Active | Cost Share for 3535277 | 30110 | 12 | (blank) | 3535277 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209378 | Active | Cost Share for 2522921 Hildret | 20868 | 12 | (blank) | 2522921 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209379 | Active | Cost Share for 2522921 CoECORE | 20868 | 12 | (blank) | 2522921 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209439 | Active | Cost Share for 2581575 | 20985 | 12 | (blank) | 2581575 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209444 | Active | Cost Share for 2574629 | 20985 | 12 | (blank) | 2574629 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209448 | Active | Cost Share for 2510246 Ford | 20249 | 12 | (blank) | 2510246 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209453 | Active | Cost Share for 2511257 | 20169 | 12 | (blank) | 2511257 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209464 | Active | Cost Share for 2510245 | 21577 | 12 | (blank) | 2510245 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209650 | Active | Cost Share B for 2555807 | 20527 | 12 | (blank) | 2555807 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209683 | Active | Cost Share for 2574745 | 20985 | 12 | (blank) | 2574745 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209705 | Active | Cost Share for 2581847 | 20985 | 12 | (blank) | 2581847 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209732 | Active | Cost Share for 3535564 EPA | 30073 | 12 | (blank) | 3535564 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209753 | Active | Cost Share for 2581859 | 20269 | 12 | (blank) | 2581859 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209769 | Active | Cost Share for 3535503 | 30073 | 12 | (blank) | 3535503 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209841 | Active | Cost Share for 3535551 | 30200 | 12 | (blank) | 3535551 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209933 | Active | Cost Share for 2582035 | 20985 | 12 | (blank) | 2582035 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61209959 | Active | Cost Share for 2570183 | 20138 | 12 | (blank) | 2570183 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61250790 | Active | CF SOM-PEDS-COSTSHAREFOR258011 | 20269 | 12 | (blank) | 2580113 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61257085 | Active | CF COST SHARE FOR 2570009 | 20138 | 12 | (blank) | 2570009 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61261020 | Active | CF COST SHARE FOR 2580321 | 20269 | 12 | (blank) | 2580321 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61267786 | Active | CF COST SHARE FOR 2591055 | 21580 | 12 | (blank) | 2591055 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61273997 | Active | CF Cost Share for 3533818 | 30094 | 12 | (blank) | 3533818 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61276108 | Active | CF COST SHARE FOR 2580775 | 20932 | 12 | (blank) | 2580775 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61276410 | Active | CF COST SHARE FOR 3534167 | 30063 | 12 | (blank) | 3534167 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61278040 | Active | CF COST SHARE FOR 2521681ROBIN | 20197 | 12 | (blank) | 2521681 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61278492 | Active | CF COST SHARE FOR 3538250 | 30063 | 12 | (blank) | 3538250 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61280804 | Active | CF COST SHARE FOR 3538125 | 30063 | 12 | (blank) | 3538125 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61281361 | Active | CF COST SHARE FOR 2580900 | 20932 | 12 | (blank) | 2580900 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61289133 | Active | CF COST SHARE FOR 2550116 | 20527 | 12 | (blank) | 2550116 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61290790 | Active | SOM-PEDS-CostShareFor2580113 | 20269 | 12 | (blank) | 2580113 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61290804 | Active | Cost Share for 3538125 | 30063 | 12 | (blank) | 3538125 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61291020 | Active | Cost share for 2580321 | 20269 | 12 | (blank) | 2580321 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61291098 | Active | Cost Share for 3535739 | 30108 | 12 | (blank) | 3535739 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61291142 | Active | Cost Share for 2513343 | 20249 | 12 | (blank) | 2513343 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61291145 | Active | Cost Share for 2555941 | 20522 | 12 | (blank) | 2555941 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61291361 | Active | Cost Share for 2580900 | 20932 | 12 | (blank) | 2580900 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61292588 | Active | Cost Share for 2550161 | 30160 | 12 | (blank) | 2550161 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61292589 | Active | CF Cost Share for 2550161 | 30160 | 12 | (blank) | 2550161 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61293997 | Active | Cost Share for 3533818 | 30094 | 12 | (blank) | 3533818 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61296108 | Active | Cost Share For 2580775 | 20932 | 12 | (blank) | 2580775 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61296410 | Active | Cost Share for 3534167 | 30063 | 12 | (blank) | 3534167 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61297085 | Active | Cost Share for 2570009 | 20138 | 12 | (blank) | 2570009 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61297786 | Active | Cost share for 2591055 | 21580 | 12 | (blank) | 2591055 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61298040 | Active | Cost Share for 2521681Robinson | 20197 | 12 | (blank) | 2521681 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61298492 | Active | Cost Share for 3538250 | 30063 | 12 | (blank) | 3538250 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
61299133 | Active | Cost Share for 2550116 | 20527 | 12 | (blank) | 2550116 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)

## C1
FISCAL_YEAR | ACCOUNTING_PERIOD_NUM | POSN_DEPT_ID | EMPLOYEE_NAME | EMPLOYEE_ID | POSITION_NUM | ERN_CODE | DEDUCTION_CODE | PAY_PERIOD_END_DATE | AMT | ACCT_CODE | ACCT_DESC | SPEEDTYPE_KEY | PROJ_ID | PGM_CODE | FUND_CODE | DEPT_ID | JOURNAL_ID | JOURNAL_DATE | JB_CODE
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 | RGS |  | 2016-01-14 | -69525 | 400100 | FAC FTP PAY | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  | CKSMDB | 2016-01-14 | -2736.06 | 418420 | FAC FTP HEALTH INS | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  | STNDRD | 2016-01-14 | -23.1 | 418421 | FAC FTP LIFE INS | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  | CUDNTB | 2016-01-14 | -74.55 | 418422 | FAC FTP DENTAL INS | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  | LTDTIA | 2016-01-14 | -49.8 | 418423 | FAC FTP DISAB INS | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  | 401A | 2016-01-14 | -5992.12 | 418433 | FAC FTP OTH RTRPL | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
2016 | 6 | 20952 | SZEFLER M.D.,STANLEY J | 227858 | 00608391 |  |  | 2016-01-14 | -1001.5 | 418434 | FAC FTP MEDICARE | 61041794 |  | 27868 | 10 | 20714 | PET1168945 | 2015-12-31 | 1101
** PET approved date, not pay end date

## C3
The highlighted "Payroll Transactions" lines are the variance between CIW's Summay table and CIW's payroll detail table.

## C4
DEPTTREE_LEVEL06_DESC | FISCAL_YEAR | ACCOUNTING_PERIOD_NUM | SumOfACTUALS_AMT | SumOfPAYROLL_ENCUMBERED_AMT | Accumulated Payroll Encumbrance
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 1 | 1192749.21 | 12377035.07
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 2 | 1169836.88 | -1386203.05
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 3 | 1328885.04 | -417393.76
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 4 | 1471023.08 | -969933.53
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 5 | 1217551.7 | -1231328.05
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 6 | 1191621.45 | -8372176.68 | 0
H0050 -- H-SOM-FM-FAMILY MEDICINE | 2016 | 7 | 1196909.66 | 0 | 0
Payroll encumbrance amount should not be zero for Dec or Jan.

## C7 & 8
* GL_Project_Tbl only has EPC description field (currently all blank). It should have EPC code field.

## C9
Projects with no EPC coding in GL_Proj_Tbl

## C10
FISCAL_YEAR | ACCOUNTING_PERIOD_NUM | POSN_DEPT_ID | DEPT_DESC | EMPLOYEE_NAME | EMPLOYEE_ID | POSITION_NUM | ERN_CODE | DEDUCTION_CODE | PAY_PERIOD_END_DATE | AMT | ACCT_CODE | ACCT_DESC | SPEEDTYPE_KEY | FUND_CODE | DEPT_ID | PGM_CODE | PROJ_ID | SUBCLASS_CODE | ACTIVITY_ID | JOURNAL_ID | JOURNAL_DATE | JB_CODE | PROCESS_INSTANCE | CU_PET_NEW_TRNS_ID
2016 | 4 |  |  | SPRUNGER M.D.,DAVID BRYAN | 104166 | 00684754 | RES |  | 2015-07-31 | -4746.5 | 403010 | MDRS OTH PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PETR344507 | 2015-10-01 | 3103 | 2004195
2016 | 4 |  |  | SPRUNGER M.D.,DAVID BRYAN | 104166 | 00684754 | RES |  | 2015-09-30 | -4746.5 | 403010 | MDRS OTH PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PETR344507 | 2015-10-01 | 3103 | 2004195
2016 | 3 | 20361 | SOM-GME ADMINISTRATION | SPRUNGER, DAVID BRYAN | 104166 | 00684754 | RES |  | 2015-09-30 | 4746.5 | 403010 | MDRS OTH PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001177 | 2015-09-30 | 3103 | 1984953
2016 | 4 |  |  | SPRUNGER M.D.,DAVID BRYAN | 104166 | 00684754 |  |  | 2015-07-31 | -363.11 | 422850 | MD RS OTH BEN | 62023201 | 20 | 20361 | 19611 |  |  |  | PETR344507 | 2015-10-01 | 3103 | 2004195
2016 | 4 |  |  | SPRUNGER M.D.,DAVID BRYAN | 104166 | 00684754 |  |  | 2015-08-31 | -363.11 | 422850 | MD RS OTH BEN | 62023201 | 20 | 20361 | 19611 |  |  |  | PETR344507 | 2015-10-01 | 3103 | 2004195
2016 | 4 |  |  | SPRUNGER M.D.,DAVID BRYAN | 104166 | 00684754 |  |  | 2015-09-30 | -363.1 | 422850 | MD RS OTH BEN | 62023201 | 20 | 20361 | 19611 |  |  |  | PETR344507 | 2015-10-01 | 3103 | 2004195
2016 | 3 | 20361 | SOM-GME ADMINISTRATION | SPRUNGER, DAVID BRYAN | 104166 | 00684754 |  |  | 2015-09-30 | 363.1 | 422850 | MD RS OTH BEN | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001177 | 2015-09-30 | 3103 | 1984953
2016 | 3 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | RGS |  | 2015-09-30 | 7777.31 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001177 | 2015-09-30 | 1101 | 1984953
2016 | 3 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | VAC |  | 2015-09-30 | 6666.24 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001177 | 2015-09-30 | 1101 | 1984953
2016 | 4 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | RGS |  | 2015-10-31 | 10777.12 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001190 | 2015-10-30 | 1101 | 2012445
2016 | 4 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | VAC |  | 2015-10-31 | 3666.43 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001190 | 2015-10-30 | 1101 | 2012445
2016 | 5 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | RGS |  | 2015-11-30 | 13110.3 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001201 | 2015-11-30 | 1101 | 2027981
2016 | 5 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 | VAC |  | 2015-11-30 | 1333.25 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001201 | 2015-11-30 | 1101 | 2027981
2016 | 6 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK,CAROL M | 108677 | 00609007 | RGS |  | 2015-12-31 | 14443.55 | 400100 | FAC FTP PAY | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY1164873 | 2015-12-31 | 1101 | 2053417
2016 | 3 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 |  | ANTMDB | 2015-09-30 | 547.21 | 418420 | FAC FTP HEALTH INS | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001177 | 2015-09-30 | 1101 | 1984953
2016 | 4 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 |  | ANTMDB | 2015-10-31 | 547.21 | 418420 | FAC FTP HEALTH INS | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001190 | 2015-10-30 | 1101 | 2012445
2016 | 5 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK, CAROL M | 108677 | 00609007 |  | ANTMDB | 2015-11-30 | 547.21 | 418420 | FAC FTP HEALTH INS | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY0001201 | 2015-11-30 | 1101 | 2027981
2016 | 6 | 20295 | SOM-RAD GENERAL OPERATIONS | RUMACK,CAROL M | 108677 | 00609007 |  | ANTMDB | 2015-12-31 | 547.21 | 418420 | FAC FTP HEALTH INS | 62023201 | 20 | 20361 | 19611 |  |  |  | PAY1164873 | 2015-12-31 | 1101 | 2053417
The Employee's position home department ID is missing

## Charfield Attributes
In attributes section above, should have hyper link to vierw program attributes. This is not available for Budget Office users